# The Decision

Given road closures at time t, which truck delivers what supplies to which shelters over the next 48 hours, and what need goes unmet?

# Who Decides

The primary user is a county Emergency Operations Center (EOC) logistics coordinator. The tool provides clear visibility into suggested routes, allows manual overrides (which remain subject to hard constraints), and delivers updated operational plans in minutes.

# Time Window

Planning origin: 3:05 p.m. EDT / 19:05 UTC on September 28, 2022 (Hurricane Ian landfall). Operational horizon: 48 hours. The coordinator re-runs the optimization model dynamically as road status updates arrive.

# Sites Overview

The system evaluates 6 designated emergency shelters and 3 supply depots across Lee County. Detailed geographic profiles and public facility baselines are moved to Appendix: Detailed Site Profiles.

# Numerical Inputs & Demand Calculations

The model tracks three critical commodity types over the 48-hour planning horizon:

- Bottled Water: 2 cases per person / 48 hours (1 case = 24 x 500 mL bottles = 12 L; 2 cases = 24 liters per person / 48h)

- MREs (Meals Ready-to-Eat): 6 meals per person / 48 hours

- Emergency Cots: 1 cot per person

Supply needs are calculated explicitly using simulated shelter populations for September 2022:

| Shelter Facility | Simulated Pop. | Water (Cases) | MREs (Meals) | Cots (Units) |
| --- | --- | --- | --- | --- |
| 1. Island Coast HS | 1,750 | 3,500 | 10,500 | 1,750 |
| 2. Hertz Arena | 6,200 | 12,400 | 37,200 | 6,200 |
| 3. Dunbar HS | 1,600 | 3,200 | 9,600 | 1,600 |
| 4. South Fort Myers HS | 1,550 | 3,100 | 9,300 | 1,550 |
| 5. Estero Rec Center | 1,200 | 2,400 | 7,200 | 1,200 |
| 6. Gateway HS | 1,900 | 3,800 | 11,400 | 1,900 |
| Total Demand | 14,150 | 28,300 | 84,900 | 14,150 |

Warehouse operating assumptions are defined as simulated relief depots based at public commercial facilities during the September 2022 response period:

| Depot Facility | Simulated Fleet | Water Stock | MRE Stock | Cot Stock |
| --- | --- | --- | --- | --- |
| Amazon RSW5 | 12 Box Trucks | 12,000 cases | 40,000 meals | 6,000 cots |
| Costco #351 | 8 Box Trucks | 10,000 cases | 30,000 meals | 4,000 cots |
| Fort Myers Whse City | 5 Box Trucks | 4,000 cases | 10,000 meals | 2,000 cots |
| Total Available Stock | 25 Box Trucks | 26,000 cases | 80,000 meals (Shortfall: 4,900 meals) | 12,000 cots |

Fleet vehicles consist of standardized 26-foot box trucks with a payload capacity of ~4,500 kg (10,000 lbs) and usable volume of ~45 m³ (~1,600 cu ft). Payload validations confirm capacity limits for 1,000 cases of water (~13,000 kg total, weight-constrained), 3,500 MREs (~4,200 kg, ~14 m³), or 500 cots (~3,500 kg, ~25 m³), as well as equivalent mixed pallet volumes.

# Repeat Trips & Operational Limits

Trucks are permitted to complete repeat turnaround trips between depots and shelters within the 48-hour planning window. Fleet routing models account for fixed operational overhead: loading time at depots is estimated at 45 minutes per vehicle, unloading time at shelters is estimated at 30 minutes, and individual driver shift limits are enforced at a maximum of 12 consecutive hours before mandatory rest.

# Priority & Fairness Criteria

Maximize the minimum percentage of each supply need met among reachable shelters, subject to inventory, truck capacity, and travel time. Report unreachable shelters separately with their full unmet need and an escalation flag.

When land routes are severed, the system automatically triggers an air-support recommendation and flags state/federal mutual aid requests for supplemental supply drops or amphibious transport. Note that air-support and mutual-aid flags serve strictly as advisory recommendations for emergency management teams.

# Constraints & System Output

Hard Constraints: Available depot inventory, vehicle volume/weight capacities, and impassable flooded roads cannot be violated.

Required System Output: The dispatch view displays optimized truck routes, compromised network bottlenecks, explicit supply allocations per facility, and rationale for routing decisions.

# Success Criterion

For a scenario with 150 available meals and 2 reachable shelters needing 100 and 200 meals (total demand 300), the system outputs a route plan delivering 50 and 100 meals respectively—achieving a uniform 50% demand satisfaction across both reachable shelters while flagging the remaining deficit for external aid.

# Appendix: Detailed Site Profiles

## 1. Emergency Shelters (Lee County)

Shelter 1: Island Coast High School

- Coordinates: 26° 43′ 40″ N, 81° 55′ 48″ W (26.72778° N, 81.93000° W)

- Simulated Population (Sep 2022): 1,750 occupants

Shelter 2: Hertz Arena

- Coordinates: 26° 26′ 26″ N, 81° 46′ 44″ W (26.44056° N, 81.77889° W)

- Simulated Population (Sep 2022): 6,200 occupants

Shelter 3: Dunbar High School

- Coordinates: 26° 38′ 15″ N, 81° 50′ 28″ W (26.63750° N, 81.84111° W)

- Simulated Population (Sep 2022): 1,600 occupants

Shelter 4: South Fort Myers High School

- Coordinates: 26° 31′ 59″ N, 81° 49′ 40″ W (26.53306° N, 81.82778° W)

- Simulated Population (Sep 2022): 1,550 occupants

Shelter 5: Estero Recreation Center

- Coordinates: 26° 26′ 04″ N, 81° 47′ 55″ W (26.43444° N, 81.79861° W)

- Simulated Population (Sep 2022): 1,200 occupants

Shelter 6: Gateway High School

- Coordinates: 26° 34′ 31″ N, 81° 43′ 50″ W (26.57528° N, 81.73056° W)

- Simulated Population (Sep 2022): 1,900 occupants

## 2. Supply Depots & Public Baselines

- Public facility baselines reflect commercial locations as of September 2026; operational supply stocks, vehicle counts, and loading limits represent simulated relief assumptions for the September 2022 event. Facility locations and map references are verified via Google Maps source links. Disclaimer: Map links and baseline location data are provided for geographic reference only and do not constitute official operational endorsement.

- Amazon Delivery Station RSW5: 8250 Logistics Dr, Fort Myers, FL 33912 (26.52722° N, 81.77833° W). Public commercial logistics hub.

- Costco Wholesale (#351): 10088 Gulf Center Dr, Fort Myers, FL 33913 (26.51472° N, 81.77958° W). Public retail warehouse club.

Fort Myers Warehouse City: 2024 Beacon Manor Dr, Fort Myers, FL 33907 (26.56722° N, 81.86944° W). Private commercial industrial park.